## Progress Tracker
GAN CHIP — DLA Engine: Progress Tracker
Track A · Team FindingSRAM · GF180MCU 180 nm · LibreLane RTL-to-GDS · updated 2026-07-04
OVERALL STATUS - DESIGN COMPLETE, FULL-CHIP SIGN-OFF (2026-07-04). Stage 1: dla_engine_top hardened WITH all 11 GF180 SRAM macros (DRC/LVS 0, antenna 0/0, setup +15.12 ns / hold +0.150 ns @ 40 ns, 9 corners, 3.3 V std cells). Stage 2: chip_top on the 2935x2935 um workshop-slot padring - Magic + KLayout DRC 0, chip-level LVS 0 (71,668 devices), antenna 0/0, GDS XOR 0, setup +21.67 ns / hold +0.329 ns. Post-layout GLS renders the MNIST digit bit-exact. Open: confirm 3.3 V slot bias & package with wafer.space; demo video; bring-up on returned silicon.
# | Task | Status | Done % | Notes
1 · Architecture & RTL Design
1 | GAN MLP architecture & MNIST proof-of-concept | Done | 100% | Pretrained FC-GAN (csinva/gan-vae); 64-256-256-784, ReLU/ReLU/tanh
2 | PE / MAC unit (dla_pe.v) - 8bx8b -> 24b accumulate | Done | 100%
3 | 4x4 PE array (dla_pe_array) - output-stationary broadcast grid | Done | 100% | 16 PEs; K-deep temporal accumulation
4 | Buffer banks - register path (USE_SRAM=0) | Done | 100% | Kept as documented fallback config
5 | Buffer banks - SRAM path (USE_SRAM=1, 11 macros: A4/B4/C3) | Done | 100% | Verified in sim + GLS; C = 3 byte-planes of the 24-bit word
6 | DLA controller FSM + writeback | Done | 100% | IDLE->CLEAR->COMPUTE(K)->DONE
7 | K=4 -> K=256 accumulation depth (native GAN layer width) | Done | 100% | Param-only RTL change; no new macros; re-hardened & re-verified
8 | Serial bridge + chip_core (4-wire link; 53 signals -> 7 pads) | Done | 100% | SCLK/MOSI/CS_N/MISO + busy/done/wb_done direct status
2 · Verification
9 | Unit TBs: d3004, d3004n4 (N=4/K=256, all 4 A/B macros), g3005 | Done | 100% | All PASS vs Python goldens
10 | g300 MNIST GAN end-to-end sim - SRAM path (USE_SRAM=1) | Done | 100% | Full 784-px digits rendered bit-exact (seeds 4, 5)
11 | Chip-level serial-bridge TB (drives pads like external host) | Done | 100% | d3004n4 goldens through SCLK/MOSI/MISO/CS_N; found+fixed READ_C timing bug
12 | Post-layout GLS of hardened netlist (unit + full GAN image) | Done | 100% | Bit-exact: routed netlist == RTL function
3 · Stage 1 RTL-to-GDS - dla_engine_top + 11 SRAM macros (SIGNED OFF)
13 | Synthesis (3.3 V AS std cells, K=256) | Done | 100% | 93,172 instances incl. 11 SRAM macros
14 | Floorplan & macro placement | Done | 100% | Die 1600x1500 um (2.4 mm2); density 63
15 | CTS & routing (Metal5 enabled; heuristic diode insertion) | Done | 100%
16 | Antenna closure | Done | 100% | 0 nets / 0 pins (density sweep; DEF-identical re-run = reproducible)
17 | Magic DRC / Netgen LVS | Done | 100% | 0 / 0
18 | STA - 9 corners @ 40 ns (25 MHz) | Done | 100% | setup +15.12 ns / hold +0.150 ns
4 · Stage 2 - padring integration (chip_top, workshop slot)
19 | Serial bridge RTL + chip_core + pin allocation (20 bidir pads) | Done | 100% | 2935x2935 um slot; single-supply 3.3 V by construction
5 · Stage 2 - full-chip sign-off (SIGNED OFF)
20 | Full 83-stage Chip flow (synth -> PnR -> GDS) | Done | 100% | runs/full_flow; macro @ [500,500]; incl. STA pad-liberty + async-input SDC fixes
21 | Chip DRC / LVS / antenna / XOR | Done | 100% | Magic 0, KLayout 0; LVS 0 (71,668 devices); antenna 0/0; XOR 0
22 | Chip STA - 9 corners @ 40 ns | Done | 100% | setup +21.67 ns / hold +0.329 ns; power ~0.27 mW; worst IR drop 0.31 mV
23 | Weight storage: weights stream from host over serial link | Done | 100% | On-chip SRAM = working tiles (2,816 B); ~280 KB INT8 streams per image
6 · Documentation & Submission
24 | Proposal slide (Chipathon template) | Done | 100%
25 | Pin requirement (Chipathon template) | Done | 100% | Updated 2026-07-04 to the workshop-slot serial-bridge pin map
26 | Schematic review slide | Done | 100% | Refresh with final chip_top recommended (deck shows interim core)
27 | Layout review slide | Done | 100% | Refresh with final chip_top recommended (deck shows interim core)
28 | Padring proposal (size & pin counts) | Done | 100% | Superseded by the signed-off chip_top GDS
29 | Demo video (8-10 min, 16:9, MP4 H.264) | Not Started | 0%
7 · Tapeout & post-silicon
30 | Confirm 3.3 V slot supply bias + package with wafer.space | In Progress | 25% | Chip is single-supply 3.3 V (DVDD=VDD shorted on-die); pads foundry-characterized at 3.3 V
31 | Post-silicon bring-up plan (host, protocol, test ladder) | Done | 100% | Bit-bang 3.3 V MCU host (Pico/ESP32); 5-step ladder up to full MNIST digit render
32 | Bring-up on returned silicon | Not Started | 0% | Test >= 2 samples; current-limited power-on first (expect << 1 mA)
Overall completion